## Project Planner
Using Virtual Reality to Control a Swarm of Drones
| Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 23 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
| ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | time axis 2017-05-31 to 2017-08-04
 | time axis 2017-05-31 to 2017-08-04
| Gantt Chart | 1 | 1 | 1 | 6 | 100%
Finalized on MATLAB Computer Vision Software | Pick Vision Software | 1 | 3 | 1 | 1 | 100%
Finalized at IRIS Drones on combination of Mission Planner and Dronekit-Python | Pick Drone Type + Software | 1 | 3 | 1 | 3 | 100%
| Design Inteface | 3 | 1 | 3 | 2 | 100%
| Acquire VR Setup | 3 | 17 | 3 | 18 | 100%
| Acquire Vision Software | 3 | 14 | 4 | 8 | 100%
| Skeleton VR Code | 4 | 1 | 4 | 1 | 100%
| Skeleton Vision Code | 4 | 1 | 4 | 1 | 100%
| VR Interface | 5 | 11 | 5 | 12 | 50%
| Vision Processing Code (VR) | 13 | 7 | 10 | 12 | 90%
| Air Worthniess Review | 16 | 12
| Vision Processing Code (MATLAB) | 16 | 15 | 11 | 15 | 90%
| Test Oculus Component | 20 | 25 | 23 | 1 | 1%
| Test Flight 1 | 28 | 1
| Review Code 1 | 29 | 6
| Test Flight 2 | 34 | 1
| Review Code 2 | 35 | 8
| Final Test Flight | 42 | 1
| Make Program Portable | 43 | 7
| Final paper | 43 | 7
| OutBrief | 48 | 1