## Project Planner
Using Virtual Reality to Control a Swarm of Drones
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | 2017-05-31 | 2017-06-01 | 2017-06-02 | 2017-06-05 | 2017-06-06 | 2017-06-07 | 2017-06-08 | 2017-06-09 | 2017-06-12 | 2017-06-13 | 2017-06-14 | 2017-06-15 | 2017-06-16 | 2017-06-19 | 2017-06-20 | 2017-06-21 | 2017-06-22 | 2017-06-23 | 2017-06-26 | 2017-06-27 | 2017-06-28 | 2017-06-29 | 2017-06-30 | 2017-07-03 | 2017-07-04 | 2017-07-05 | 2017-07-06 | 2017-07-07 | 2017-07-10 | 2017-07-11 | 2017-07-12 | 2017-07-13 | 2017-07-14 | 2017-07-17 | 2017-07-18 | 2017-07-19 | 2017-07-20 | 2017-07-21 | 2017-07-24 | 2017-07-25 | 2017-07-26 | 2017-07-27 | 2017-07-28 | 2017-07-31 | 2017-07-01 | 2017-07-02 | 2017-07-03 | 2017-07-04
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48
Gantt Chart | 1 | 1 | 1 | 1 | 100%
Pick Vision Software | 1 | 3 | 1 | 1 | 100%
Pick Drone Type + Software | 1 | 3 | 1 | 1 | 50%
Design Inteface | 3 | 1
Order Hardware | 3 | 14
Acquire Vision Software | 4 | 1
Skeleton VR Code | 4 | 1
Skeleton GC Code | 4 | 1
Skeleton Vision Code | 5 | 1
Skeleton Program Interface | 5 | 1
Drone Control (VR) | 6 | 2
Drone Control (GC) | 6 | 2
Swarm Control (VR) | 8 | 2
Swarm Control (GC) | 9 | 5
Test Oculus Component | 14 | 3
Vision Processing (GC) | 17 | 11
Vision Processing (MATLAB) | 17 | 2
Vision Processing (VR) | 17 | 2
Air Worthniess Review | 17 | 14
Test Flight 1 | 31 | 1
Review Code 1 | 31 | 5
Test Flight 2 | 36 | 1
Review Code 2 | 37 | 5
Test Flight 3 | 42 | 1
Do Final Presentation | 43 | 1